## New
Functionality Break-down | UI | UI Comments | DB | DB Comments | Service
Project Context Card
Display Context Card | 12 |  | 8 | Table creation- no draft/pub just single copy | 8
Save & log functionality | 8 |  | 4 |  | 8
Excel download | 2 |  |  |  | 16
Code Review & Testing | 4 |  | 4 |  | 4
| 26 |  | 16 |  | 36 | Full | 210 | 138 | 200
Risk Assessment | [6 empty] | 26.25 | 17.25 | 25
Check List
Display Check List | 16 | UI complex - dropdown in px data table component | 6 | Table creation and Backend data loading | 6 | Till RR | 134 | 81 | 108
Save & log functionality | 8 |  | 8 | Data updating procedure | 6 | Days | 16.75 | 10.125 | 13.5
| 24 |  | 14 |  | 12
Risk Register
Risk Register Template | 12 |  | 6 | Fetch 'Y' value items from checklist table | 6
Import Risks | 4 |  | 8 | Risk register tbl creation for Draft and Publish | 4
Master tables creation for dropdowns |  |  | 4
Add, Edit & Remove row in RR Template | 8 | Edit and delete icon for all rows.Empty row at the end for add. | 4 | Insert/Delete procedure to register table for new manual data entry | 4
Filters and sort in each column. Filters by red, yellow, green colors | 12 | Need R&D on color filter
log functionality | 4 |  | 4 |  | 4
Excel download | 2 |  | NA |  | 16
Edit RR Template | NA |  | NA | Possible at UI end to multiply values at real time and populate it in the column? | NA
Code Review & Testing | 4 |  | 4 |  | 4
Layover message on page load | 4
| 50 |  | 30 |  | 38
Risk Register Data Form - Risk Assessment & Risk Treatment
Display RR Data Form | 16 |  | 8 | To fetch existing data from register table for particular record-Dataform view | 6
Risk Priority Calculation & form validation if any | 8 |  | 4 |  | 4
Save and publish Data Form | 6 |  | 5 | Edit and update procedure for dataform view | 8
Code Review & Testing | 4 |  | 4 |  | 4
| 34 |  | 21 |  | 22
Opportunity Register
Display Opportunity Register Template | 8 |  | 8 | Table creation Save Draft and Publish,data loading and display, Master tables for DD | 6
Add, Edit & Remove row in RR Template | 8 | Edit and delete icon for all rows.Empty row at the end for add. | 4 | Insert/Delete procedure to register table for new manual data entry | 4
log functionality | 4 |  | 8 |  | 4
Excel download | 2 |  | NA |  | 8
Filter & Sort | 0 |  | NA
Code Review & Testing | 4 |  | 4 |  | 4
| 26 |  | 24 |  | 26
Opportunity Register Data Form
Display OR Data Form | 16 |  | 4 | To fetch existing data from register table for particular record-Dataform view | 8
Opportunity Priority Calculation & form validation if any | 8 |  | 4 |  | 4
Submit and Publish Data Form | 4 |  | 5 | Edit and update procedure for dataform view.Insert/Delete procedure to Opp table for new manual data entry | 8
Code Review & Testing | 4 |  | 4 |  | 4
| 32 |  | 17 |  | 24
Score card for reference | 6 | Image display |  | Will require table creation and data loading- No Static image | 4
Probability Matrix
Display Risk vs opportunity | 6 | Image Display | 8 | Static Image | 4
Code Review & Testing | 2 |  |  |  | 2
| 8 |  | 8 |  | 6
Massive Download | 4 |  |  |  | 32

## Sheet3
1 | Priyanka | Shwetha | Neha
2 | Ayushi | Anand | Balaji
3 | Mohammed | Vaibhav
|  |  | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-04
Checklist | UI | bar: 2018-04-25 to 2018-04-27
| Service |  | 2018-04-26: 1; 2018-04-30: 3
DB | bar: 2018-04-26 to 2018-04-27
Risk Register | UI |  | 2018-04-30: 1; 2018-05-02: 1; 2018-05-03: 1; 2018-05-04: 1; 2018-05-07: 3; 2018-05-08: 3
| Service |  | 2018-05-02: 3; 2018-05-03: 3; 2018-05-04: 3; 2018-05-07: 3; 2018-05-08: 3
DB | bar: 2018-04-30; 2018-05-02 to 2018-05-04
Risk Data Form | UI |  | 2018-05-02: 2; 2018-05-03: 2; 2018-05-04: 2; 2018-05-07: 2; 2018-05-08: 2
Service | bar: 2018-05-07 to 2018-05-09
| DB |  | 2018-05-02: 2; 2018-05-03: 2; 2018-05-04: 2
Context Card | UI |  | 2018-05-09: 2; 2018-05-10: 2; 2018-05-11: 2
Service | bar: 2018-05-10 to 2018-05-15
DB | bar: 2018-05-07 to 2018-05-09
Opportunity Register | UI |  | 2018-05-09: 3; 2018-05-10: 3; 2018-05-11: 3
| Service |  | 2018-05-10: 2; 2018-05-11: 2; 2018-05-14: 2
| DB |  | 2018-05-07: 2; 2018-05-08: 2; 2018-05-09: 2
Opportunity data Form | UI |  | 2018-05-14: 2; 2018-05-15: 2; 2018-05-16: 2; 2018-05-17: 2
| Service |  | 2018-05-15: 2; 2018-05-16: 2; 2018-05-17: 2
| DB |  | 2018-05-10: 2; 2018-05-11: 2
Probability Matrix | UI |  | 2018-05-14: 3; 2018-05-15: 3
Service | bar: 2018-05-16 to 2018-05-17
DB | bar: 2018-05-10 to 2018-05-11
Score card for reference | UI |  | 2018-05-18: 2; 2018-05-21: 2
| Service |  | 2018-05-18: 2
Massive Download | UI |  | 2018-05-18: 3
Service | bar: 2018-05-18 to 2018-05-23
Open Questions
Setup for Anand and Mohammed